## Slide 1
MILESTONE 6
Garden / Explore
restructure
A phased plan
Heirlooms · groundwork before Milestone 7 (delivery)

## Slide 2
Where we are
Roughly two weeks of work since the project began at the end of April 2026.
SHIPPED
NOW
THIS DECK
FUTURE
M0
Domain
30 Apr
M1
Uploader
early May
M2
Server
early May
M3
Self-hosted
deployment
early May
M4
Settings &
organisation
v0.16, mid May
M5
Capsules
in progress
M6
Garden /
Explore
this work
M7
Delivery
future
M8
Multi-user
future

## Slide 3
Why this matters
The Garden tab today is one flat surface trying to do two jobs.
Loading everything every time is slow. The mental model conflates doing work (tagging, processing, composting) with exploring memories (browsing what you've kept). Different jobs, different emotional registers, different places.
Milestone 7 (delivery) needs a settled Garden structure to land in. Multi-user (Milestone 8+) will compound the scaling problem if left. Doing this work now nips several decisions in the bud — at lower cost than retrofitting later.
Today's problem
One Garden tab. Slow loads as the dataset grows. Workflow and leisure mixed. No clear answer to "what is this page for?"
What we're building
Garden = work surface (plots: "Just arrived" + user-defined). Explore = leisure surface (paginated, filterable). Two clear jobs, two clear places.

## Slide 4
A new Milestone 6
Why this is being delivered before the originally-planned Milestone 6 (delivery).
Delivery needs a settled foundation
Milestone 6 (now Milestone 7) is the most emotionally resonant feature of the product. It deserves to land on a settled Garden / Explore structure rather than a flat surface that's about to change shape.
Loading and register problems compound
Every increment delayed makes the flat-Garden problem worse. The dataset is growing; the brand-register conflation is being built into more features each cycle.
Multi-user makes retrofit expensive
Many decisions here (plot ownership, pagination, photo-detail variants) are easier to design correctly the first time than to retrofit after multi-user lands. Now is the cheap moment.
Nips decisions in the bud
Brand-register, scaling, capsule-picker source, vocabulary — several open questions converge on this work. Better to settle them once, in one increment, than to keep deferring.
How the remaining milestones have been renumbered
Before
M5 Capsules (in progress)
M6 Milestone delivery
M7 Multi-user access
After
M5 Capsules (in progress)
M6 Garden / Explore restructure
M7 Milestone delivery
M8 Multi-user access

## Slide 5
The plan at a glance
Four deliverables, ~3-4 days total. Tools first as a safety net.
1
~1 DAY
Tools
Re-import utility. Scan GCS, hash content, recreate uploads rows. A safety net for the rest of M6.
1A · 1B · 1C
2
~1 DAY
Backend + Explore basic
EXIF extraction. Pagination. Plot schema. New /explore route with paginated grid.
2A · 2B · 2C
3
~1-1.5 DAYS
Web complete
Explore filters and sort. Garden plots restructure. Photo detail variants per surface.
3A · 3B · 3C
4
~1 DAY
Android adoption
Android Explore tab. Android Garden plots. Bottom-nav restructure (burger menu).
4A · 4B · 4C

## Slide 6
Deliverable 1
Tools — re-import utility
Independent of the rest of M6. Built first as a safety net: with this in place, the rest of the work can experiment freely with the schema and data.
1A
Scan and import
Standalone script lists every object in the GCS bucket, computes SHA256, and INSERTs an uploads row for each. Content stays in place; rows reference existing GCS keys.
≈ 0.5 day
1B
Trigger and verify
Fires EXIF backfill jobs for imported rows (no-op if EXIF hasn't shipped yet). Verifies counts match GCS object count. Sample integrity check.
≈ 0.25 day
1C
Document
Runbook in PA_NOTES.md: how to nuke the database safely, run the script, and confirm recovery. Bret can do this without re-uploading.
≈ 0.25 day
Three sub-tasks · Shipped as one focused session

## Slide 7
Deliverable 2
Backend + Explore basic
All backend foundations plus the simplest possible Explore route. Garden's existing flat behaviour unchanged during this deliverable.
2A
EXIF extraction
Background job on upload. Adds taken-date and location lat/lng columns to uploads (nullable). Item appears immediately; metadata populates asynchronously.
≈ 0.4 day
2B
Pagination + /explore
Cursor-based pagination on list endpoints. New /explore route serving a paginated grid, newest-first by upload date. No filters yet.
≈ 0.3 day
2C
Plot schema
New tables for plot definitions and per-user configuration. "Just arrived" is system-defined; user-defined plots layer on top. Sort/filter API additions.
≈ 0.3 day
Three sub-tasks · Shipped as one focused session

## Slide 8
Deliverable 3
Web complete
Web fully transitioned to the new Garden / Explore structure. The flat-Garden mental model retires; users learn the new shape.
3A
Explore filters and sort
Tag, date range, capsule membership, composted toggle, location-boolean. Sort options (newest/oldest by upload, by taken date) with EXIF-availability indicator.
≈ 0.4 day
3B
Garden plots
Garden becomes vertically-stacked horizontal rows. Mandatory "Just arrived" plot at top; user-defined plots below via "Add a plot" affordance with tag-based criteria.
≈ 0.6 day
3C
Photo detail variants
Detail view differs by entry surface: Garden = action affordances prominent; Explore = content presentation. Compost heap link stays on Garden.
≈ 0.3-0.5 day
Three sub-tasks · Shipped as one focused session

## Slide 9
Deliverable 4
Android adoption
Android catches up to the new web structure, including the bottom-nav restructure that replaces v0.21.0's three-tab Settings entry.
4A
Android Explore tab
New tab matching web's Explore. Reuses photo detail components where possible. Pagination via Compose's LazyColumn / LazyRow primitives.
≈ 0.4 day
4B
Android Garden plots
Garden tab restructured to match web: horizontal-scrolling plot rows (LazyRow within LazyColumn). User plot management mirroring web.
≈ 0.4 day
4C
Bottom-nav restructure
Settings moves out of bottom nav into a burger menu. Bottom nav becomes Garden / Explore / Capsules. Three tabs, cleaner, brand-quiet.
≈ 0.2 day
Three sub-tasks · Shipped as one focused session

## Slide 10
Sequence and dependencies
What blocks what, and what can run any time.
INDEPENDENT
1
Tools
No dependencies. Run any time.
Recommended first — gives a safety net for the rest of the work.
SEQUENTIAL
2
Backend + Explore basic
Foundations
→
3
Web complete
Needs 2C (plot schema)
→
4
Android adoption
Needs web design language settled
Notes
Web Explore (in Deliverable 2) ships before Garden plots (Deliverable 3) starts in earnest — Explore acts as the user fallback during the Garden transition.
Android (Deliverable 4) waits for web (Deliverable 3) so the design patterns are settled before the Compose implementation begins.

## Slide 11
Rough timescales
Software estimates are unreliable; treat these as ranges, not commitments.
One engineer
Sequential — deliverable by deliverable
5 – 7
weeks
Four deliverables × ~1+ week each + review and buffer. The honest traditional baseline.
Two engineers
Parallel where dependencies allow
3 – 5
weeks
Backend and web can overlap; D4 (Android) waits for the web design language to settle.
Three engineers
Maximum useful parallelism
3 – 4
weeks
Backend, web, and Android split across three. Diminishing returns past three given the deliverable dependencies.
Buffer for review, debugging, and post-deploy fixes is included. Real elapsed time will depend on how many context-switch costs land between increments.

## Slide 12
Velocity
Why traditional estimates feel high — and a more honest reframe.
SOLO, SPARE TIME
~1 year
Evenings and weekends. The pace a single founder typically moves at on a side project.
FOUNDER + AI
~9 days
End of April to 8 May. The project to date — backend, web, Android, brand work, ~49 integration tests for capsules alone.
What this means for Milestone 6
SESSION 1
Tools
Re-import utility. Safety net for the rest of M6.
SESSION 2
Backend + Explore basic
EXIF, pagination, plot schema, basic /explore route.
SESSION 3
Web complete
Filters, Garden plots, photo detail variants. Flat-Garden retires.
SESSION 4
Android adoption
Explore tab, Garden plots, burger-menu nav.
Founder owning context across sessions; tight scoping; AI doing the typing while the founder steers. The multiplier is perceived for this product and team, not a benchmarked claim.

## Slide 13
What's next
Settle four small questions, then draft Phase 1A.
1
Plot configuration scope
Single-user only at v1, or schema set up for per-user plots from the start (foreshadowing multi-user)? Affects 1C's table design.
2
Vocabulary doc timing
IDIOMS.md updates (plot, Just arrived, negative-action separation principle) land with Phase 1, Phase 2, or as their own doc-only patch.
3
Plot criteria language
v1: tag-matching only (simplest), or richer queries (date ranges, "in capsule X")? Affects Phase 3B.
4
v0.21.0 sequencing
v0.21.0 Android ships first as currently scoped, then this milestone begins. v0.21.0 nav structure changes during Phase 4 — users see two nav structures in close succession (acceptable).
Phase 1A — EXIF extraction — drafted as the first concrete brief once these are settled.